## README
FinOps project timeline
Thesis-annex working view, 28 September 2026
Field | Meaning
Project | FinOps Cloud Data Platform: generator, local POC and Databricks/GCP implementation
Period | 1–30 September 2026
Gantt dates | Documented activity windows or proposed work windows; they are not measured effort.
Cloud dates | 27 September marks the date of the written Belgium status, not a verified execution timestamp.
Original baseline | The 5 September Azure-oriented workbook is retained separately as the initial plan.
Use in thesis | Use the Gantt with its evidence legend; do not present reported cloud runs as independently verified.
Evidence status | Interpretation
Local validated | Local test or validation results recorded; no claim about cloud execution.
Documented | Dated planning, code or repository evidence; completion beyond that is not inferred.
Cloud reported | Workspace run described in the Belgium completion note; run-level artifacts are still needed.
Planned | Next step or deadline; no execution claimed.
Detailed planning | The WBS sheet lists task-level work. Daily Gantt shows all 30 days of September.
Date interpretation | Documented windows reconstruct dated activity; they are not time logs. Report checkpoints are not execution dates.
Daily view | Daily markers are formula-driven by WBS start and finish dates. The weekly Gantt remains the compact thesis figure.
Outstanding evidence | Cloud runs, total platform costs and final submission stay planned or reported until primary records are checked.

## Gantt
Project Gantt
Week-level overview; dates and evidence status are shown at left
ID | Work package | Start | Finish | Evidence | 2026-09-01 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28
P01 | Framing and initial architecture | 2026-09-01 | 2026-09-06 | Documented | ■
P02 | Generator and monthly bills | 2026-09-04 | 2026-09-19 | Local validated | ■ | ■ | ■
P03 | Local POC and datamarts | 2026-09-07 | 2026-09-19 | Local validated | ■ | ■ | ■
P04 | Cloud model and Job code | 2026-09-19 | 2026-09-20 | Documented |  |  | ■
P05 | Belgium configuration reported | 2026-09-27 | 2026-09-27 | Cloud reported |  |  |  | ■
P06 | DEV/PROD backfill reported | 2026-09-27 | 2026-09-27 | Cloud reported |  |  |  | ■
P07 | First Daily DEV run reported | 2026-09-27 | 2026-09-27 | Cloud reported |  |  |  | ■
P08 | Complete Daily DEV-to-PROD proof | 2026-09-28 | 2026-09-29 | Planned |  |  |  |  | ■
P09 | Classic monthly-close proof | 2026-09-28 | 2026-09-29 | Planned |  |  |  |  | ■
P10 | Databricks and GCP cost attribution | 2026-09-28 | 2026-09-29 | Planned |  |  |  |  | ■
P11 | Thesis evidence and figures | 2026-09-27 | 2026-09-30 | Documented |  |  |  | ■ | ■
P12 | Final submission | 2026-09-30 | 2026-09-30 | Planned |  |  |  |  | ■
S1–S6 | Source notes and limits are in the Sources sheet.

## Milestones
Project milestones
Documented, reported and planned checkpoints
ID | Date | Checkpoint | Evidence | Source
M01 | 2026-09-05 | Research framing documented | Documented | S1
M02 | 2026-09-20 | Cloud Gold and datamart code documented | Documented | S4
M03 | 2026-09-27 | Generator and monthly history validated locally | Local validated | S2
M04 | 2026-09-27 | Local POC results documented | Local validated | S3
M05 | 2026-09-27 | Belgium monthly backfill described | Cloud reported | S5
M06 | 2026-09-27 | First Daily DEV load described | Cloud reported | S5
M07 | 2026-09-29 | Collect Daily DEV-to-PROD proof | Planned | S5
M08 | 2026-09-29 | Collect Classic monthly-close proof | Planned | S5
M09 | 2026-09-29 | Assemble comparable cloud-cost evidence | Planned | S5
M10 | 2026-09-30 | Final thesis submission | Planned | S1

## Sources
Evidence and limitations
The status column in the Gantt refers to these source records
ID | Record | What it supports and does not support
S1 | Initial project baseline, 5 September 2026 | Early scope, planning dates and 30 September deadline. It remains the original Azure-oriented plan, not the current completion record.
S2 | Cloud reorganization note, 19 September; local validation record, 27 September | Separation of generator, POC and cloud projects; local Daily and monthly dataset checks.
S3 | Thesis evidence register and local validation record, 27 September | Local DuckDB/datamart and dashboard checks. Does not establish Databricks execution.
S4 | Cloud reorganization note, 19–20 September | Gold/Datamart code and local unit tests; integration execution was still pending in that note.
S5 | Databricks Belgium completion plan, 27 September | Reports monthly DEV/PROD backfill and first Daily DEV load. Job/Run IDs, outputs and actual run dates are not indexed there. Subsequent tasks are proposed.
S6 | Thesis assembly and illustration plans, 27 September | Documents the 37-section manuscript structure and planned figures; not a completed PDF.
Note | The 27 September cloud entries are documentation checkpoints. Replace them with verified run dates only after the Databricks evidence is collected.

## WBS
Work breakdown structure
Updated task inventory for September 2026; evidence status is separate from schedule
WBS | Task | Track | Start | Finish | Evidence | Date basis | Source | Output or limitation
0.1 | Frame the problem and scope | Framing | 2026-09-01 | 2026-09-05 | Documented | Documented window | S1 | Initial formulation; later cloud scope differs.
0.2 | Set research questions and method | Framing | 2026-09-01 | 2026-09-06 | Documented | Documented window | S1 | Initial academic package.
0.3 | Outline requirements and acceptance criteria | Framing | 2026-09-02 | 2026-09-06 | Documented | Documented window | S1 | Initial requirements, subject to revision.
0.4 | Draft logical architecture and stack options | Framing | 2026-09-02 | 2026-09-06 | Documented | Documented window | S1 | Original Azure-oriented baseline.
1.1 | Profile reference FOCUS samples | Generator | 2026-09-01 | 2026-09-04 | Documented | Documented window | S1 | Source profiling in the initial plan.
1.2 | Implement deterministic Daily generation | Generator | 2026-09-04 | 2026-09-07 | Local validated | Documented window | S2 | Validated later in the local history.
1.3 | Build monthly billing simulator | Generator | 2026-09-06 | 2026-09-08 | Local validated | Documented window | S2 | Monthly no-change and scenario logic.
1.4 | Generate Daily and monthly history | Generator | 2026-09-07 | 2026-09-19 | Local validated | Documented window | S2 | 18 no-change monthly bills documented.
1.5 | Validate Daily and monthly files | Generator | 2026-09-19 | 2026-09-27 | Local validated | Documented window | S2 | 27 September local validation record.
2.1 | Implement local medallion pipeline | Local POC | 2026-09-07 | 2026-09-14 | Local validated | Documented window | S3 | Local execution only.
2.2 | Publish DuckDB model and datamarts | Local POC | 2026-09-10 | 2026-09-14 | Local validated | Documented window | S3 | 14 local analytical subjects.
2.3 | Build local Streamlit dashboard | Local POC | 2026-09-13 | 2026-09-14 | Local validated | Documented window | S3 | Local AppTest and query checks.
2.4 | Reconcile local analytical outputs | Local POC | 2026-09-14 | 2026-09-27 | Local validated | Documented window | S3 | Synthetic January POC results.
3.1 | Separate generator, POC and cloud code | Cloud platform | 2026-09-19 | 2026-09-19 | Documented | Documented window | S4 | Three sibling projects.
3.2 | Implement cloud Gold and datamart SQL | Cloud platform | 2026-09-19 | 2026-09-20 | Documented | Documented window | S4 | Local code and tests; cloud output separate.
3.3 | Define cloud pipeline and audit modules | Cloud platform | 2026-09-19 | 2026-09-20 | Documented | Documented window | S4 | Local code state.
3.4 | Configure Belgium RAW and catalogs | Cloud platform | 2026-09-27 | 2026-09-27 | Cloud reported | Report checkpoint | S5 | Actual setup dates need confirmation.
3.5 | Configure Belgium storage and compute | Cloud platform | 2026-09-27 | 2026-09-27 | Cloud reported | Report checkpoint | S5 | Classic migration reported.
3.6 | Backfill monthly data in DEV | Cloud platform | 2026-09-27 | 2026-09-27 | Cloud reported | Report checkpoint | S5 | Run ID and control output still needed.
3.7 | Backfill monthly data in PROD | Cloud platform | 2026-09-27 | 2026-09-27 | Cloud reported | Report checkpoint | S5 | Run ID and control output still needed.
3.8 | Load first Daily file in DEV | Cloud platform | 2026-09-27 | 2026-09-27 | Cloud reported | Report checkpoint | S5 | PROD promotion not established here.
3.9 | Validate Daily DEV-to-PROD promotion | Cloud platform | 2026-09-28 | 2026-09-29 | Planned | Proposed | S5 | Collect both task outputs.
3.10 | Test Classic monthly close | Cloud platform | 2026-09-28 | 2026-09-29 | Planned | Proposed | S5 | Requires a real monthly billing file.
3.11 | Test replay and idempotence | Cloud platform | 2026-09-29 | 2026-09-29 | Planned | Proposed | S5 | Compare rows and costs before and after.
3.12 | Collect OPS and reconciliation outputs | Cloud platform | 2026-09-29 | 2026-09-29 | Planned | Proposed | S5 | Capture environment and Run IDs.
4.1 | Attribute Databricks DBUs to runs | Platform cost | 2026-09-28 | 2026-09-29 | Planned | Proposed | S5 | Separate All-Purpose and Serverless usage.
4.2 | Collect GCP VM and storage charges | Platform cost | 2026-09-28 | 2026-09-29 | Planned | Proposed | S5 | Needed for total Classic cost.
4.3 | Compare compute scenarios fairly | Platform cost | 2026-09-28 | 2026-09-29 | Planned | Proposed | S5 | Hold workload and output constant.
5.1 | Draft framing and architecture chapters | Thesis | 2026-09-04 | 2026-09-27 | Documented | Documented window | S6 | Draft sections exist, not final PDF.
5.2 | Draft implementation and analysis chapters | Thesis | 2026-09-20 | 2026-09-28 | Documented | Documented window | S6 | Evidence still to be reconciled.
5.3 | Prepare ERD and evidence figures | Thesis | 2026-09-28 | 2026-09-29 | Planned | Proposed | S6 | Insert simplified ERD in section 4.5.2.
5.4 | Prepare project-management appendix | Thesis | 2026-09-28 | 2026-09-29 | Planned | Proposed | S6 | Export the summary Gantt with legend.
5.5 | Proofread references and final PDF | Thesis | 2026-09-29 | 2026-09-29 | Planned | Proposed | S6 | Review factual and layout issues.
5.6 | Submit manuscript | Thesis | 2026-09-30 | 2026-09-30 | Planned | Proposed | S1 | Deadline in initial project baseline.

## Daily Gantt
Daily Gantt
Task-level planning across 1–30 September 2026; see WBS and README for date basis
WBS | Task | Start | Finish | Evidence | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30
0.1 | Frame the problem and scope | 2026-09-01 | 2026-09-05 | Documented | bar: 2026-09-01 to 2026-09-05
0.2 | Set research questions and method | 2026-09-01 | 2026-09-06 | Documented | bar: 2026-09-01 to 2026-09-06
0.3 | Outline requirements and acceptance criteria | 2026-09-02 | 2026-09-06 | Documented | bar: 2026-09-02 to 2026-09-06
0.4 | Draft logical architecture and stack options | 2026-09-02 | 2026-09-06 | Documented | bar: 2026-09-02 to 2026-09-06
1.1 | Profile reference FOCUS samples | 2026-09-01 | 2026-09-04 | Documented | bar: 2026-09-01 to 2026-09-04
1.2 | Implement deterministic Daily generation | 2026-09-04 | 2026-09-07 | Local validated | bar: 2026-09-04 to 2026-09-07
1.3 | Build monthly billing simulator | 2026-09-06 | 2026-09-08 | Local validated | bar: 2026-09-06 to 2026-09-08
1.4 | Generate Daily and monthly history | 2026-09-07 | 2026-09-19 | Local validated | bar: 2026-09-07 to 2026-09-19
1.5 | Validate Daily and monthly files | 2026-09-19 | 2026-09-27 | Local validated | bar: 2026-09-19 to 2026-09-27
2.1 | Implement local medallion pipeline | 2026-09-07 | 2026-09-14 | Local validated | bar: 2026-09-07 to 2026-09-14
2.2 | Publish DuckDB model and datamarts | 2026-09-10 | 2026-09-14 | Local validated | bar: 2026-09-10 to 2026-09-14
2.3 | Build local Streamlit dashboard | 2026-09-13 | 2026-09-14 | Local validated | bar: 2026-09-13 to 2026-09-14
2.4 | Reconcile local analytical outputs | 2026-09-14 | 2026-09-27 | Local validated | bar: 2026-09-14 to 2026-09-27
3.1 | Separate generator, POC and cloud code | 2026-09-19 | 2026-09-19 | Documented | bar: 2026-09-19
3.2 | Implement cloud Gold and datamart SQL | 2026-09-19 | 2026-09-20 | Documented | bar: 2026-09-19 to 2026-09-20
3.3 | Define cloud pipeline and audit modules | 2026-09-19 | 2026-09-20 | Documented | bar: 2026-09-19 to 2026-09-20
3.4 | Configure Belgium RAW and catalogs | 2026-09-27 | 2026-09-27 | Cloud reported | bar: 2026-09-27
3.5 | Configure Belgium storage and compute | 2026-09-27 | 2026-09-27 | Cloud reported | bar: 2026-09-27
3.6 | Backfill monthly data in DEV | 2026-09-27 | 2026-09-27 | Cloud reported | bar: 2026-09-27
3.7 | Backfill monthly data in PROD | 2026-09-27 | 2026-09-27 | Cloud reported | bar: 2026-09-27
3.8 | Load first Daily file in DEV | 2026-09-27 | 2026-09-27 | Cloud reported | bar: 2026-09-27
3.9 | Validate Daily DEV-to-PROD promotion | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
3.10 | Test Classic monthly close | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
3.11 | Test replay and idempotence | 2026-09-29 | 2026-09-29 | Planned | bar: 2026-09-29
3.12 | Collect OPS and reconciliation outputs | 2026-09-29 | 2026-09-29 | Planned | bar: 2026-09-29
4.1 | Attribute Databricks DBUs to runs | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
4.2 | Collect GCP VM and storage charges | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
4.3 | Compare compute scenarios fairly | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
5.1 | Draft framing and architecture chapters | 2026-09-04 | 2026-09-27 | Documented | bar: 2026-09-04 to 2026-09-27
5.2 | Draft implementation and analysis chapters | 2026-09-20 | 2026-09-28 | Documented | bar: 2026-09-20 to 2026-09-28
5.3 | Prepare ERD and evidence figures | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
5.4 | Prepare project-management appendix | 2026-09-28 | 2026-09-29 | Planned | bar: 2026-09-28 to 2026-09-29
5.5 | Proofread references and final PDF | 2026-09-29 | 2026-09-29 | Planned | bar: 2026-09-29
5.6 | Submit manuscript | 2026-09-30 | 2026-09-30 | Planned | bar: 2026-09-30